## Sheet1
№ | Launching Tesla into space
1 | Estimate the volume and complexity of the work |  | 8757 hours | (8700 + 16000 + 4 * 9000) /6 = 10116 (10116)
1.1 |  | Goal | 72 hours | (65 + 130 + 4 * 72)/6 = 79
1.2 |  | Risk Assessment | 160 hours | (150 + 270 + 4 * 160)/6 = 176
1.3 |  | Writing project documentation | 6600 hours | (6400 + 13000 + 4 * 6700)/6 = 7653
1.4 |  | Development of metrics for the project | 1925 hours | (1850 + 3600 + 4 * 1950)/6 = 2208
2 | Identify the necessary resources and sources of their receipt |  | 9151 hours | (8300 + 18000 + 4 * 9000)/6 = 10083 (10083)
2.1 |  | Drawing up a financial plan | 336 hours | (230 + 560 + 4 * 360)/6 = 383
2.2 |  | Search for investors | 6795 hours | (6200 + 12000 + 4 * 6700) /6 = 7500
2.3 |  | Identify sources of resource delivery | 2020 hours | (1800 + 3600 + 4 * 1968) / 6 =2200
3 | The architecture and design of the rocket |  | 17556 hours | (16000 + 30000 + 4 * 16500) / 6 = 18666 (18666)
3.1 |  | Development of technical characteristics of the rocket | 720 hours | (650 + 1400 + 4 * 700) / 6 = 825
3.2 |  | Development of rocket design | 1450 hours | (1250 + 2700 + 4 * 1350) / 6 = 1558
3.3 |  | Determination of rocket components | 10250 hours | (9000 + 18000 + 4 * 10000) /6 =10700
3.4 |  | Modeling and prototyping of a rocket | 5136 hours | (4500 + 9000 + 4 * 5000) / 6 = 5583
4 | Construction of a rocket |  | 8790 hours | (8400 + 17000 + 4 * 8800) / 6 = 10100
5 | Software testing and verification of calculations |  | 17900 hours | (16500 + 30000 + 4 * 17000) / 6 = 17416
6 | Preparation for takeoff |  | 9 hours | (6 + 18 + 4 * 10) / 6 = 11 (11)
6.1 |  | Delivery of a rocket to the take-off area | 5 hours | (3 + 7 + 4 * 5) / 6 = 5
6.2 |  | Mounting the rocket | 2 hours | (1 + 3 + 4 * 2) / 6 = 2
6.3 |  | Delivery of Tesla to the rocket | 1 hours | (1 + 4 + 4 * 2) / 6 = 2
6.4 |  | Loading Tesla into a rocket | 1 hours | (1 + 4 + 4 * 2) / 6 = 2
7 | Rocket launch |  | 1 hours | (1 + 4 + 4 * 2) / 6 = 2
|  |  | 62164 hours | 66394 hours
(1 optimistic + 1 pessimistic + 4 real) / 6

## Sheet2
№ | Title
1 | Planning and Control
1.1 | Determine the scope and risks and identify the objectives of testing.
1.2 | Determine the required test resources like people, test environments etc.
1.3 | Schedule test analysis and design tasks, test implementation, execution and evaluation.
2 | Analysis and Design
2.1 | Review the test basis. The test basis is the information on which test cases are based, such as requirements, design specifications, product risk analysis, architecture and interfaces
2.2 | Identify test conditions
2.3 | Design the tests
2.4 | Design the test environment set-up and identify the required infrastructure and tools
3 | Implementation and Execution:
3.1 | Develop and prioritize test cases by using techniques and create test data for those tests.
3.2 | Create test suites from the test cases for efficient test execution.Test suite is a collection of test cases that are used to test a software program
3.3 | Re-execute the tests that previously failed in order to confirm a fix.
3.4 | Log the outcome of the test execution. A test log is the status of the test case (pass/fail).
3.5 | Compare actual results with expected result.
4 | Evaluating Exit criteria and Reporting:
4.1 | Assess if more test are needed or if the exit criteria specified should be changed
4.2 | Write a test summary report for stakeholders
5 | Test Closure activities:
5.1 | Check which planned deliverables are actually delivered and to ensure that all incident reports have been resolved
5.2 | Finalize and archive testware such as scripts, test environments, etc. for later reuse
5.3 | Handover the testware to the maintenance organization. They will give support to the software
5.4 | Evaluate how the testing went and learn lessons for future releases and projects

## Sheet3
Regression
Total | Closed Issues | Reopen Issues | Reopen Rate, % | Decline Issues | Decline Rate, % | Blocked | Blocked Rate, % | Critical | Major
207 | 196 | 68 | 26 | 23 | 12 | 7 | 2,9 | 13 | 14
It is recommended to pay attention to regression testing in connection with a large number of bugs found in previously implemented and tested functionality
New functional
Total | Closed Issues | Reopen Issues | Reopen Rate, % | Decline Issues | Decline Rate, % | Blocked | Blocked Rate, % | Critical | Major
154 | 121 | 30 | 19 | 14 | 11 | 8 | 1,9 | 6 | 2
Decline Rate = (Decline Issues/Closed Issues)*100 %
Decline Rate = (23/196)*100%
Reopen Rate =(Reopen Bugs+Closed Bugs) /Reopen Bugs *100%
Reopen Rate =(68/(68+196))*100%
Blocked Rate = (Total/Blocked)*100%
Blocked Rate= (207/7)*100%
Decline Rate = (Decline Issues/Closed Issues)*100 %
Decline Rate = (14/121)*100%
Reopen Rate =(Reopen Bugs+Closed Bugs) /Reopen Bugs *100%
Reopen Rate =(30/ (30+121))*100%
Blocked Rate = (Total/Blocked)*100% | [9 empty] | По всем дефектам | [5 empty] | По новим дефектам
Blocked Rate= (154/8)*100% | [9 empty] | Статус | Количество | Критич | Висок | Средн | Мин | Статус | Количество | Критич | Висок | Средн | Мин
[10 empty] | Исправл | 280 | 30 | 70 | 100 | 80 | Исправл | 28 | 3 | 7 | 10 | 8
| описать результаты рассчетов | [8 empty] | провер | 170 | 50 | 20 | 50 | 50 | провер | 17 | 5 | 2 | 5 | 5
| построить графики | [8 empty] | откр зан. | 20 | 0 | 10 | 10 | 0 | откр зан. | 2 | 0 | 1 | 1 | 0
[10 empty] | Найдено. | 360 | 50 | 110 | 80 | 120 | Найдено. | 36 | 5 | 11 | 8 | 12
| dashboard в джире | [8 empty] | Отклон | 40 | 0 | 0 | 10 | 30 | Отклон | 4 | 0 | 0 | 1 | 3
1.9